## Large Group SAG
Illinois Energy Efficiency Stakeholder Advisory Group (SAG)
Issue Tracker
2018-2019 Large Group SAG Meetings
Tracker Updated: 12/9/19
Tracker Overview: The purpose of this document is to track open issues and follow-up from Large Group SAG meetings, including summarizing follow-up items, information requests, and action items from each meeting. This document will also include responses to open items and provide for when issues are "closed." If needed, the SAG Facilitator will follow-up to seek clarification. Issues addressed by SAG Subcommittees and SAG Working Groups will also be tracked by the SAG Facilitator. Visit the SAG website (www.ILSAG.info) to review the agenda, meeting materials and meeting notes for each meeting included in the Issue Tracker.
November 19-20, 2019 SAG Meetings
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open / Closed / Postponed
Water-Energy Nexus | Alliance for Water Efficiency and ComEd | SAG Facilitator to follow-up with ComEd on sharing water study results / green stormwater infrastructure report when finalized. | N/A | Closed
Utility Q3 Updates | ComEd, Ameren IL, Peoples Gas & North Shore Gas | 1) Stakeholders are interested in more information about qualifying customers based on bill payment history; Ameren IL previously piloted this. The new contractor (Slipstream) can share how customers are qualified in other jurisdictions. SAG Facilitator to schedule OBF for discussion in 2020. 2) SAG Facilitator to add statewide programs to the list for discussion in 2020 (planning process). 3) See pages 10-11 of notes for specific follow-up questions for PG & NSG. SAG Facilitator will follow-up with PG & NSG to answer open questions. | N/A
EE Considerations for Recreational Cannabis | MEEA | A follow-up teleconference meeting will be scheduled in early 2020, specifically to discuss: Navigant presentation on cannabis measure research compared to IL-TRM. MEEA update on cannabis considerations. | During Q1 2020 | N/A
Cumulative Persisting Annual Savings (Nov. 20) | NRDC, ComEd and Ameren IL Presenters | SAG Facilitator will discuss open policy questions further with Ameren IL and ComEd and circulate an updated list in advance of the next meeting. | Dec. 2019
November 12-13, 2019 EM&V Work Plan SAG Teleconference Meetings
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open / Closed / Postponed
Non-Qualified Equipment Policy Request | Navigant | SAG participants on the Nov. 12th call generally agreed with evaluators counting/verifying savings from non-qualified equipment. Navigant will draft a summary of the proposed resolution and send to the SAG Facilitator for circulation to SAG for 10 Business Day review/comment. a. If any substantive questions or concerns are raised about the proposed resolution, a call will be scheduled in early January. If no concerns are raised about the proposed resolution, the resolution will be documented on the SAG website – https://www.ilsag.info/policy/ b. This policy issue needs to be finalized in time for the 2020 evaluation process to begin in late January. | 2019-12-01
Additional Follow-Up Items from Nov. 12 Meeting | Navigant | a. Non-Energy Impacts: Additional information will be provided to the SAG Non-Energy Impacts Working Group on which programs Navigant selects for additional NEI research, and the results of Navigant’s secondary research. A Working Group meeting is anticipated in Q1 2020. b. Electric Utility 3rd Party Programs: SAG Facilitator will schedule a report-out on 3rd party programs in 2020. c. Income Eligible/Income Qualified NTG Research: A discussion needs to be scheduled with SAG regarding whether NTG research is completed on the product discounts program. SAG Facilitator to follow-up with Navigant. | TBD
September 17, 2019 SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open / Closed / Postponed
Innovative Energy Efficiency Trends | Dan York, ACEEE | Several SAG participants were interested in the EPRI report Kevin Dick (Delta Institute) mentioned. Visit the SAG website to download the report: http://www.ilsag.info/mm_2019_9_17.html | N/A | Closed
Gas Technology Innovations: Focus on Gas-fired Heat Pumps | Paul Glanville, Gas Technology Institute (GTI) | 1) Gas Heat Pump Roadmap is in development by 15 utilities. SAG Facilitator to follow-up with GTI on whether it would be useful for the final roadmap to be presented to SAG at a future meeting. 2) GTI has an income qualified project in Rockford. SAG Facilitator to follow-up with GTI for more information on this project.
Energy Foundry: Background and EE Innovation Trends | Damien Despinoy, Energy Foundry | No action items. | N/A | N/A
Intellihot Technologies | Scott Lenger, Intellihot | No action items. | N/A | N/A
C&I Networked Lighting Controls: Technology Capabilities and Energy Savings Potential | Chris Neme and Dan Mellinger, Energy Futures Group | No action items. | N/A | N/A
ComEd Energy Efficiency Emerging Technologies Update | Mark Milby, ComEd | No action items. | N/A | N/A
Nicor Gas Emerging Technology Update | Randy Opdyke, Nicor Gas | No action items. | N/A | N/A
General follow-up item: SAG Facilitator to look for ways for SAG to be more intentional on discussing workforce development approaches and opportunities.
August 28, 2019 SAG Teleconference Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open / Closed / Postponed
ComEd Mid-Year Portfolio Rebalancing | Molly Lunn, ComEd | ComEd will provide a table that breaks down the original plan budget for income eligible programs, and the updated budget per mid-year portfolio shifting.
August 7, 2019 SAG Teleconference Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open / Closed / Postponed
Net-to-Gross (NTG) for Low Income Programs | Jennifer Morris, ICC Staff; Molly Lunn, ComEd | 1) SAG Facilitator will send NTG policy language to the Policy Manual Version 2.0 negotiating parties for review. If any objections are received to including in Version 2.0, a policy meeting will be scheduled this fall with the goal of reaching interim agreement, documenting on the SAG website, and adding this policy topic to the list for a future Policy Manual update. 2) Navigant will incorporate updated draft policy language in the IL-NTG Methods attachment, which will be circulated to SAG for review (anticipated within the next week). | Goal is to resolve by Sept. 12, 2019 (the date when TRM V8 will be finalized)
Counting Behavior Savings for Nicor Gas Program | Ted Weaver, First Tracks Consulting, on behalf of Nicor Gas | If there are any questions or concerns about the approach Nicor Gas described to counting savings for the new Nicor Gas behavioral program, please reach out to Ted Weaver (weaver_t@mindspring.com) and CC Celia@CeliaJohnsonConsulting.com. If needed, a follow-up discussion will be scheduled. | Questions or concerns due by COB on 8/21 | Closed. ICC Staff and NRDC expressed concern over the timing proposal for the new Nicor Gas behavioral program. Nicor Gas reviewed stakeholder concerns and decided not to pursue the alternative proposal; their behavioral program will follow the calendar year schedule with Navigant.
May 14, 2019 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open / Closed / Postponed
Addressing Equity, Diversity and Inclusion | Walker-Miller Energy Services; MEEA; Ameren Illinois; ComEd | SAG Facilitator will review written feedback and coordinate with Income Qualified EE Advisory Committee facilitator on suggested topics for future discussion. | During 2nd quarter of 2019
February 25, 2019 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open / Closed / Postponed
Health and Energy Efficiency | Will Klein, Green and Healthy Homes Initiative | 1) A follow-up teleconference webinar will be scheduled for GHHI to present more information on healthcare funding sources. 2) SAG Facilitator question: Should this topic be further addressed in SAG? If so, what are you interested in discussing? Thoughts and feedback are welcomed. | 1) Schedule within the next 3 months 2) Send feedback by April 1. | Closed - the SAG follow-up call on health + EE funding is scheduled on Tuesday, June 11.
ComEd Quarterly Summary Presentation | Julie Hollensbe, ComEd | • Kristol Simms, Ameren IL Q: How does ComEd’s public housing program differ from what DCEO offered? o Julie Hollensbe will follow-up with Molly Lunn. |  | Closed
ComEd Research and Development Initiatives Presentation | Mark Milby, ComEd | 1) A ComEd webinar within the next month will provide additional information on selected initiatives; SAG Facilitator to distribute information to SAG. 2) ComEd is interested in presenting more information about their unique partnership with the National Renewable Energy Lab at a future SAG meeting. SAG Facilitator to add to the tracking list for consideration.
Ameren Illinois 3rd Party Programs | Kristol Simms, Ameren Illinois | Q from PowerTakeoff: Interested in feedback on response to RFP, is that an option? Ameren IL will check with Cadmus and their procurement teams on what can be provided.
January 14, 2019 Large Group SAG Teleconference Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open / Closed / Postponed
Overview of 2019 SAG Plan | Celia Johnson, SAG Facilitator | 1) Comments on the final draft 2019 SAG Plan are due by COB on Monday, January 28. If SAG participants have proposed edits, please submit them in redline directly to Celia: Celia@CeliaJohnsonConsulting.com. 2) If you are interested in joining the new Market Transformation Savings Working Group, please reach out directly to Celia by COB on Thursday, January 31: Celia@CeliaJohnsonConsulting.com. | 1) 1/28/2019 2) 1/31/2019 | Final 2019 SAG Plan posted on the website and circulated to the SAG Steering Committee on 1/31/2019. Market Transformation Savings Working Group participants will be accepted on a rolling basis.
Oveview of draft ComEd EUL Research Report, Phase 1 | Karen Maoz, Navigant | Comments on the draft report are due by COB on Friday, January 25. Send comments to Karen Maoz (karen.maoz@Navigant.com) and Jennifer Morris, ICC Staff (Jennifer.Morris@illinois.gov). If SAG participants are interested in a follow-up discussion about this EUL research, please let Karen Maoz know when submitting comments on the draft report. | 2019-01-25 | Closed
December 3-4, 2018 Large Group SAG Teleconference Meetings
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open/Closed
Ameren Illinois Evaluator - Overview of Draft EM&V Work Plan for 2019 | Zach Ross, Opinion Dynamics | 1. Business Behavior Modification Pilot: Has this program been evaluated in other jurisdictions? A: This type of program is relatively uncommon but Opinion Dynamics is looking into this. Jonathon Jackson would be happy to share more once they have information available. 2. Does the multi-family IQ initiative provide incentives for heating? Jonathon Jackson will double-check. 3. Do Community Action Agencies touch multifamily? A: No, it is primarily single family. There is a separate implementer that reaches multifamily. Opinion Dynamics will confirm. 4. Voltage Optimization: Are you considering any other approaches besides CVRf? A: VO leads are not on the phone; Opinion Dynamics will follow-up with Chris Neme, NRDC. 5. Economic and Employment Impact Study: The draft job study methodology will be presented to the SAG Non-Energy Impacts Working Group. Anticipating an end of January teleconference meeting. | TBD
ComEd Evaluator - Overview of Draft EM&V Work Plan for 2019 | Jeff Erickson, Navigant | AMI Overview: Follow-up discussion with Rob Neumann, Navigant and Rob Kelter, ELPC offline. R. Kelter is interested in how Bidgely can be used to analyze savings from various program measures. | N/A
Nicor Gas Evaluator - Overview of Draft EM&V Work Plan for 2019 | Laura Agapay-Read, Navigant | No action items. | N/A
Peoples Gas & North Shore Gas Evaluator - Overview of Draft EM&V Work Plan for 2019 | Kevin Grabner, Navigant | No action items. | N/A
November 7, 2018 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open/Closed
Industry Spotlight: Market Transformation | Stacey Paradis, MEEA; Jim Fay, ComEd; Randy Opdyke, Nicor Gas; and Christina Pagnusat, Peoples Gas & North Shore Gas | 1. ComEd is finalizing the Market Transformation Summit Report by the end of this year. The final report will be circulated to SAG. 2. There will be a utility collaborative meeting in December (Dec. 14) to further discuss MT. If you are interested in more information, contact Celia Johnson (Celia@CeliaJohnsonConsulting.com) by Friday, December 7 and she will share your contact information with the meeting organizers. | 1. End of 2018 2. Friday, Dec. 7, 2018 | Closed
Peoples Gas & North Shore Gas Quarterly Summary (Q2-Q3) | Christina Pagnusat and Omayra Garcia, Peoples Gas & North Shore Gas | Chris Neme Q: Why are only 1/3 of customers getting weatherization recs? What is the follow through on the 1/3 that do receive recs, do they actually complete the weatherization? Peoples Gas & North Shore Gas will follow-up with this information. | End of 2018
Nicor Gas Quarterly Summary (Q2-Q3) | Chris Vaughn, Nicor Gas | No action items. | N/A | N/A
Ameren Illinois Quarterly Summary (Q2-Q3) | Kristol Simms, Ameren Illinois | HEIQ program (multi-family) – 5,000 residences participated; 2,500 low income and 2,500 moderate income. Q: How many of these are multi-family? ▪ Ameren Illinois will follow-up. ▪ Ameren Illinois will confirm that 50% of the building units need to be income eligible to participate in the IQ program. | End of 2018 | Follow-up from Ameren Illinois: What was the PY2018 planned unit participation for low income? **Income Qualified Initiative – 5,000 total (2,500 low income / 2,500 moderate income) **Multifamily Initiative – 2,500 total What does AIC utilize to confirm income eligibility to participate in the Income Qualified Initiative? ** AIC utilizes https://lihtc.huduser.gov/ list to help determine if it’s a low income type MF property.
ComEd Quarterly Summary (Q2-Q3) | Julie Hollensbe and Neal Latham, ComEd | No action items. | N/A | N/A
SAG Innovative Idea Survey | Celia Johnson, SAG Facilitator | The 2019 SAG Plan is currently in development. If you have any innovative topics that should be addressed in 2019, please fill out the survey by COB on Thursday, Nov. 29: https://www.surveymonkey.com/r/8DPMTZB | Thurs., Nov. 29 | SAG Innovative Ideas will be accepted on an ongoing basis. The survey is posted on the landing page of the SAG website.
September 18, 2018 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open/Closed
Industry Spotlight: "Equity in Energy Efficiency" | Jim Jerozal, Nicor Gas; Kristol Simms, Ameren Illinois; Lauren Casentini, Resource Innovations | 1. Celia will review feedback to develop future action items for SAG; incorporate into the 2019 SAG Plan. 2. Celia will follow-up with Industry Spotlight presenters on next steps for this topic. | End of 2018 | Closed- several equity topics will be included in the 2019 SAG Plan.
Peoples Gas – North Shore Gas Research & Development Program | Christina Pagnusat, Peoples Gas – North Shore Gas; Allen Dusault, Franklin Energy | No action items. | N/A | N/A
ComEd LED Street Lighting Program | Bill Burns, ComEd | No action items. | N/A | N/A
ComEd Voltage Optimization Program | Dan Schick and | No action items. | N/A | N/A
July 31, 2018 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open/Closed
SAG Planning Overview | Celia Johnson, SAG Facilitator | Participation in upcoming discussions: If you want to be included in the Policy Manual Subcommittee, Non-Energy Impacts Working Group, and/or Annual Template Report Working Group, please email the SAG Facilitator. | By COB on Wed., Aug. 15 | Closed
|  | Comments on 2018 SAG Plan (draft): Send comments and proposed edits directly to the SAG Facilitator. | By COB on Tuesday, August 14 | Closed
|  | Comments on SAG Process Guidance document (draft): Send comments and proposed edits directly to the SAG Facilitator. | By COB on Tuesday, August 14 | Closed
|  | Policy Manual Subcommittee: Proposed policies are due by COB on Friday, August 31 – please complete the Proposed Policy Template. Participants are encouraged not to propose substantive changes to policies already agreed upon in the existing Policy Manual, unless there is rationale to make the change. | By COB on Friday, August 31 | Closed - Policy Manual Subcommittee kick-off meeting was held on Wed., Sept. 19.
|  | SAG Website Re-Design: If you have any web developers to suggest, please send to SAG Facilitator. | By COB on Wed., Aug. 15 | Closed
ComEd EE Research & Development (R&D) Programs | Jim Fay, Noel Corral and Jim Lyon, ComEd | SAG Facilitator will schedule a presentation on ComEd’s baseline study in 2019. | N/A | A teleconference meeting will be scheduled in early fall 2019 for Itron to present ComEd's baseline study.
|  | • Q: Chris Neme – For C&I, to what extent are you assessing custom savings? o A: ComEd will discuss internally and follow-up. | N/A
Ameren Illinois Quarterly Report-Out (Q1 2018); Overview of PY9 and Transition Period Results | Kristol Simms, Ameren Illinois | • Q: Chris Neme – What is the breakdown between multi-family and single family? o A: Ameren IL will look into this and follow-up. | N/A
ComEd Quarterly Report-Out (Q1 2018); Overview of PY9 and Transition Period Results | Julie Hollensbe, ComEd | SAG Facilitator to follow-up with MEEA and ComEd on LED street lighting; this may be scheduled at SAG for future discussion. | N/A | Closed - overview of LED Street Lighting (ComEd) held during Sept. large group meeting. SAG Facilitator will follow-up with Ameren IL on whether there is interest in presenting on LED street lighting to SAG at a future meeting.
Nicor Gas Quarterly Report-Out (Q1 2018); Overview of PY6 and Transition Period Results | Chris Vaughn, Nicor Gas | No action items. | N/A
People Gas – North Shore Gas Quarterly Report-Out (Q1 2018); Overview of PY6 and Transition Period Results | Christina Pagnusat and Omayra Garcia, Peoples Gas –North Shore Gas | No action items. | N/A